## Template
Capstone A - Project Timeline
Area | Task | Task Duration | Status | Due Date | Task Owner | Notes
Research Paper Tasks
Paper Draft 1 | Literature Review for Article 1 | 4 Hours | Completed | 2021-06-24 | Student A
| Literature Review for Article 2 | 4 Hours | Completed | 2021-06-24 | Student B
| Literature Review for Article 3 | 4 Hours | Completed | 2021-06-24 | Student C
| Literature Review for Article 4 | 4 Hours | Completed | 2021-06-24 | Student B
| Literature Review for Article 5 | 4 Hours | Completed | 2021-06-24 | Student A
Refine Draft 1 | Improvise & Refine Introduction | 8 Hours |  | 2021-06-29 | Student C
| Improvise & Refine Abstract | 1 Hour |  | 2021-06-29 | Student C
| Refine of existing articles 10 from Literature Review | 2 Hours |  | 2021-06-29 | Student B
| Refine of existing articles 10 from Literature Review | 2 Hours |  | 2021-06-29 | Student A
| Refine of existing articles 10 from Literature Review | 2 Hours |  | 2021-06-30 | Student B
| Refine of existing articles 10 from Literature Review | 2 Hours |  | 2021-06-30 | Student A
| Refine of existing articles 10 from Literature Review | 2 Hours |  | 2021-06-30 | Student C
| Refine of existing articles 10 from Literature Review | 2 Hours |  | 2021-07-01 | Student B
| Refine of existing articles 10 from Literature Review | 2 Hours |  | 2021-07-01 | Student A
| Refine of existing articles 10 from Literature Review | 2 Hours |  | 2021-07-01 | Student C
| Refine of existing articles 10 from Literature Review | 2 Hours |  | 2021-07-02 | Student B
| Refine of existing articles 10 from Literature Review | 2 Hours |  | 2021-07-02 | Student A
| Methods & Misc Sections | 4 Hours |  | 2021-07-02 | Student C
Technical Tasks
Establish Relations between all nodes | Load State and County Nodes | 8 Hours | Completed |  |  | 8 Hours to learn neo4j, download/install and learn cypher syntax
| Establish State and County Relation | 3 Hours | Completed
| Load all the individual features into Graph database according to design | 3 Hours | Completed
By Loading 1st 500k records csv establish following relations | Relations Covid Cases for Process Identification | 2 Hours | Completed | 2021-06-27 | All Team Members
| Relations Covid Cases for Ethnicity | 2 Hours | Completed | 2021-06-27 | All Team Members
| Relations Covid Cases for Month | 2 Hours | Completed | 2021-06-27 | All Team Members
| Relations Covid Cases for State | 2 Hours | Completed | 2021-06-27 | All Team Members
| Relations Covid Cases for County | 2 Hours | Completed | 2021-06-27 | All Team Members
| Relations Covid Cases for Age | 2 Hours | Completed | 2021-06-27 | All Team Members
| Relations Covid Cases for Race | 2 Hours | Completed | 2021-06-27 | All Team Members
| Connections between neighboring States | Undetermined |  |  |  | Source needed
| Connections between neighboring Counties | Undetermined

## Log
Capstone - Project Timeline
Area | Task | Task Duration | Status | Due Date | Task Owner | Notes
Research Paper Tasks
Paper Draft 0
Paper Draft 1
Paper Draft 2
Technical Tasks
Area | Task | Task Duration | Status | Due Date | Task Owner | Notes